## Slide 1
Coach
Feedback
Enable
SRI-B LEADERSHIP TASK FORCE
Manager Effectiveness & Everyday Leadership
Plan for Samsung R&D Institute Bangalore managers and employees, running from June 2026 to December 2026.
SRIB
Audience: managers, first-time managers, leaders, and employees across teams
Jun-Dec
Time horizon: launch in June 2026 and institutionalize by December 2026
LMD
Partner with LMD for curriculum, toolkits, and transition support
Draft initiative plan for SRIB internal discussion
Samsung R&D Institute Bangalore | SRIB Managers and Employees | June-Dec 2026

## Slide 2
SRIB NORTH STAR
02
Make people leadership an everyday SRIB practice.
By December 2026, employees should experience clearer expectations, faster feedback, stronger coaching, and better support from their managers.
Manager effectiveness flywheel
Role clarity
What good looks like
Coach
Ask, listen, guide
Feedback
Continuous signals
Enable
Toolkits and rituals
Learn
Leader circles
For managers
A common SRIB standard for 1:1s, coaching conversations, feedback moments, and team learning routines.
For employees
More timely guidance, stronger recognition, clearer growth conversations, and fewer surprises in formal review cycles.
For leaders
Visible modeling through learning circles, walk-and-talks, skip-level listening, and monthly adoption reviews.
Outcome: SRIB managers grow people continuously while sustaining delivery excellence.
Samsung R&D Institute Bangalore | SRIB Managers and Employees | June-Dec 2026

## Slide 3
JUNE-DEC 2026 WORKSTREAMS
03
Four workstreams convert intent into SRIB manager routines.
Each workstream has a concrete artifact, operating rhythm, and owner group so the initiative can scale across SRIB teams.
1. Managers and leaders as coach
Coach-the-coach labs, leader shadowing, coaching question banks, and monthly manager practice sessions.
2. Continuous feedback culture
Replace annual-only feedback with weekly/monthly check-ins, project debriefs, feedforward prompts, and recognition moments.
3. Manager enablement toolkit
SRIB-ready 1:1 templates, team charter canvas, difficult conversation guides, onboarding checklists, and pulse survey packs.
4. Leader-led learning circles
Leaders facilitate small circles, walk-and-talks, case clinics, and peer learning to make development local and practical.
Design principle: every theme becomes a repeatable SRIB manager ritual by December 2026, not a one-time workshop.
Samsung R&D Institute Bangalore | SRIB Managers and Employees | June-Dec 2026

## Slide 4
OPERATING MODEL
04
Build with LMD, pilot inside SRIB, scale through leaders.
The task force owns direction and governance while LMD strengthens design, facilitation, and first-time manager transition support.
SRIB Task Force
Set charter, success metrics, leadership sponsorship, governance cadence.
LMD Partner
Co-design curriculum, toolkits, learning circles, and first-time manager pathway.
Business Leaders
Model behaviors, sponsor circles, identify pilot teams, review adoption data.
Managers
Run rituals: 1:1s, feedback moments, huddles, debriefs, and coaching conversations.
First-time manager transition
June-July: pre-role orientation on expectations, people responsibilities, and first 90-day moments.
August-December: buddy leader and LMD clinic for case discussion, feedback practice, and escalation support.
Governance cadence: monthly adoption review from June to December 2026, plus quarterly employee pulse.
Samsung R&D Institute Bangalore | SRIB Managers and Employees | June-Dec 2026

## Slide 5
JUNE-DEC 2026 ROADMAP
05
Start in June, prove behavior change, institutionalize by December.
The rollout creates visible wins without waiting for the annual HR or performance cycle.
Jun-Jul
Design
Finalize SRIB charter, manager behavior standard, pilot groups, and first toolkit pack.
Artifact: SRIB charter + toolkit v1
Aug-Sep
Pilot
Run coaching labs, launch continuous feedback rituals, and host leader-led learning circles.
Artifact: pilot evidence pack
Oct-Dec
Scale
Refine from pulse data, train champions, publish playbook, and align with review cycle inputs.
Artifact: SRIB scale playbook
Success measures
Manager ritual adoption, employee feedback frequency, first-time manager confidence, and pulse movement on trust and clarity.
Decision ask
Approve SRIB pilot scope, nominate leader sponsors, and authorize LMD collaboration for June-Dec 2026 execution.
Samsung R&D Institute Bangalore | SRIB Managers and Employees | June-Dec 2026